## SPRINT 61
SPRINT 61
ID | ISSUE TYPE | DESCRIPTION | STORY POINT | EPIC LINK | SPRINT STATUS | RELEASE STATUS | COMMENT
AWNL-456 | Story | DECRIP | 3 | Admin | Blocked |  |  | SPRINT STATUS |  | REALEASE PLAN
AWNL-516 | Story | Admin Portal - Transaction Table - Include fees, amount paid and outstanding column to table |  | Admin Portal & cms | Done | Ready-For-Deployment |  | To-Do | 2 | In-Progress Dev & Test | 2
AWNL-524 | Bug | Lead table export button is broken on the admin portal is broken |  |  | Done | Passed QA | Awaiting clearing of cache | Blocked | 4 | Passed QA | 1
AWNL-389 | Story | Payment - Admin Verification - Calculate Outstanding Payment | 5 | SLH-Online pyt | Done | Deployed |  | In-Development | 2 | Failed QA | 1
AWNL-532 | Story | Presentation Page- Book-a-Call - Add Functionality to Pull Book - a - Call Data on Admin portal |  | Admin portal & cms | Done | Deployed | this feature is not available in Dev yet | Ready-For-Testing | 0 | Passed Dev | 0
AWNL-533 | Bug | Role Permission (Juliet Obasanya should be delisted) |  |  | Done | Deployed | Juliet is on the list of roles. | In-Testing | 2 | Failed Dev | 0
AWNL-500 | Bug | Website Homepage Contact Us Section |  |  | Done | Deployed | This was deployed to the Live environment alone. | Done | 9 | Ready-For-Deployment | 3
AWNL-508 | Story | Presentation Page- Enable Book-a-Call Button | 8 | Website-Mkt machine | Done | Deployed | Added restriction on date and marketing menu (Lead and book a call placed under it). |  |  | Deployed | 6
AWNL-518 | Story | Bank Transfer-Add currency symbols | 1 | SLH-Online pyt | Done | Deployed | I did not get a verification email to proceed further with the registration to validate this.
AWNL-496 | Story | Admin - Notification for Student Payment via Bank Transfer | 2 | SLH-Online pyt | Done | Failed QA | I did not get a verification email to proceed further with the registration to validate this.
AWNL-525 | Story | Admin Portal - Add Account Features on Transaction Table | 2 | SLH-Hub and Admin | In-Testing | Ready-For-Deployment | No course duration on table
AWNL-511 | Story | Student Survey - Add Current Income and Target Income Fields to Survey form | 8 | SLH-Hub and Admin | In-Development | In-Progress Dev & Test
AWNL-531 | Story | Admin Portal - Transaction Table - Add Table for Additional Course | 2 | Admin portal & cms | In-Development | In-Progress Dev & Test | Incorrect labeling,should be Additional course.
AWNL-528 | Task | SLH - Change Course Videos Design |  |  | To-Do
AWNL-531 | Task | Website - New Student Enrolment, Refer and Earn scheme |  |  | To-Do |  |  | ISSUE TYPES
AWNL-537 | Bug | Optimization for All Devices (QA, Dev and Live Environment) |  |  | In-Testing | Ready-For-Deployment |  | Epic | 0
AWNL-447 | Story | Payment - Automatic Installment Payment Deduction (Auto debit) | 5 | SLH-Online pyt | Blocked |  | Installment payment field is yet to be computed on the transaction table | Story | 11
AWNL-493 | Bug | Replace Text "Test Store" with Dashboard for Paypal |  |  | Blocked |  |  | Bug | 5
AWNL-522 | Task | Website - Our process section - Write description on "Still on decided" |  |  | Blocked |  |  | Task | 3
[8 empty] | Sub-Task | 0
[8 empty] | Total Sprint Issues | 19
SPRINT VELOCITY
[8 empty] | Committed | 36
[8 empty] | Completed | 16

## SPRINT 62
SPRINT 61
ID | ISSUE TYPE | DESCRIPTION | STORY POINT | EPIC LINK | SPRINT STATUS | RELEASE STATUS | COMMENT
AWNL-456 | Story | DECRIP | 3 | Admin | Blocked |  |  | SPRINT STATUS |  | REALEASE PLAN
[8 empty] | To-Do | 0 | In-Progress Dev & Test | 0
[8 empty] | Blocked | 1 | Passed QA | 0
[8 empty] | In-Development | 0 | Failed QA | 0
[8 empty] | Ready-For-Testing | 0 | Passed Dev | 0
[8 empty] | In-Testing | 0 | Failed Dev | 0
[8 empty] | Done | 0 | Ready-For-Deployment | 0
[10 empty] | Deployed | 0
ISSUE TYPES
[8 empty] | Epic | 0
[8 empty] | Story | 1
[8 empty] | Bug | 0
[8 empty] | Task | 0
[8 empty] | Sub-Task | 0
[8 empty] | Total Sprint Issues | 1
SPRINT VELOCITY
[8 empty] | Committed | 3
[8 empty] | Completed | 0

## SPRINT - SAMPLE
SPRINT 61
ID | ISSUE TYPE | DESCRIPTION | STORY POINT | EPIC LINK | SPRINT STATUS | RELEASE STATUS | COMMENT
AWNL-456 | Story | DECRIP | 3 | Admin | Blocked | Passed QA |  | SPRINT STATUS |  | REALEASE PLAN
| Epic |  | 8 |  | Done | Failed QA |  | To-Do | 1 | In-Progress Dev & Test | 4
| Bug |  | 3 |  | In-Development | In-Progress Dev & Test |  | Blocked | 1 | Passed QA | 1
| Task |  | 5 |  | Ready-For-Testing | In-Progress Dev & Test |  | In-Development | 1 | Failed QA | 1
| Sub-Task |  | 5 |  | In-Testing | In-Progress Dev & Test |  | Ready-For-Testing | 1 | Passed Dev | 0
|  |  | 3 |  | To-Do | Ready-For-Deployment |  | In-Testing | 1 | Failed Dev | 0
|  |  | 3 |  | Done | Deployed |  | Done | 3 | Ready-For-Deployment | 1
|  |  | 5 |  | Done | Deployed |  |  |  | Deployed | 2
In-Progress Dev & Test
ISSUE TYPES
[8 empty] | Epic | 1
[8 empty] | Story | 1
[8 empty] | Bug | 1
[8 empty] | Task | 1
[8 empty] | Sub-Task | 1
[8 empty] | Total Sprint Issues | 5
SPRINT VELOCITY
[8 empty] | Committed | 35
[8 empty] | Completed | 16